## week 2
Governance Call Summary Report Template
Batch Name as per Salesforce | JSD 01_OL_AMBER 02_Orion_Barasat | Training Partner Name | Orion Edu Tech
GC of _th Week | 1 | Present Week and Day | 1 & 5 | Total Strength | 40
Batch Start Date as per Salesforce | 14.04.2023 | Domain Trainer | R Deepika | IER Score
Batch End Date as per Salesforce | 14.07.2023 |  |  | Track (On Track/Off Track)
Batch Start Date as per Curriculum | 17.04.2023 | Assistant Trainer | Khushbu Singh | IER Score
Batch End Date as per Curriculum | 17.07.2023 |  |  | Track (On Track/Off Track)
Metric | Data | Root cause for Low/High performance | Next Steps |  | Status
Attendance | Class Average: 57 % | Proloy Saha, UPAM MAZUMDER, Rajib Mohanta, Shalini Roy, Shatabdi Chouhan, Supriya Pahan, MAMUN MAHAMMAD, SERFUL SK, Abu Raihan Mondal Most of the students joined other courses and rest of them joined for job, noshows | will Drop these learners |  | G: 85% and above
| Participants in G: 23 |  |  |  | Y: 75%-85%
| Participants in Y: 8 |  |  |  | R: Below 75%
Participants in R: 9
Punctuality | Class Average: 57% | Abhijit Deb,,Pinki,Rudradip Laskar,Rajat Ghosh,Sharmila,Sagar,Md. Barjahan,Mamun Mohammad. Due to network issue and also some of the students are not able to access canvas and code academy for first 4 days | Talked with the student who is having network issue and told them to take synchronous session in mobile and asychronous session in laptop. For login issue we contacted generation team and got access for canvas and code academy for students |  | G: 85% and above
| Participants in G: 23 |  |  |  | Y: 75%-85%
| Participants in Y: 8 |  |  |  | R: Below 75%
Participants in R: 9
Grooming | Class Average: 57 | Abhijit Deb,,Pinki,Rudradip Laskar,Rajat Ghosh,Sharmila,Sagar,Md. Barjahan,Mamun Mohammad.Due to network issue and also some of the students are not able to access canvas and code academy for first 4 days | Talked with the student who is having network issue and told them to take synchronous session in mobile and asychronous session in laptop. For login issue we contacted generation team and got access for canvas and code academy for students |  | G: 85% and above
| Participants in G: 23 |  |  |  | Y: 75%-85%
| Participants in Y: 8 |  |  |  | R: Below 75%
Participants in R: 9
Dropout | Dropouts of week:0 | Proloy Saha, UPAM MAZUMDER, Rajib Mohanta, Shalini Roy, Shatabdi Chouhan, Supriya Pahan, MAMUN MAHAMMAD, SERFUL SK, Abu Raihan Mondal |  |  | G: 85% and above
| Total Dropouts till week:0 |  |  |  | Y: 75%-85%
| No Show:0 |  |  |  | R: Below 75%
Performance | Behavioral Skill |  |  |  | G: 85% and above
| Class Average 2.85 |  |  |  | Y: 75%-85%
| Participants in G: 23 |  |  |  | R: Below 75%
Participants in Y: 8
Participants in R: 9
| Mindset Skill |  |  |  | G: 85% and above
| Class Average 2.85 |  |  |  | Y: 75%-85%
| Participants in G: 23 |  |  |  | R: Below 75%
Participants in Y: 8
Participants in R: 9
| Technical Skill |  |  |  | G: 85% and above
| Class Average : 9.0 |  |  |  | Y: 75%-85%
| Participants in G : 23 |  |  |  | R: Below 75%
Participants in Y : 8
Participants in R: 9
Curriculum Progression | Curriculum day: Monday to Friday |  |  |  | G: 85% and above
| Week: 1 |  |  |  | Y: 75%-85%
| Day: 5 |  |  |  | R: Below 75%
On tract as per session plan- yes
Canvas Progression: | Canvas completion 67.78%age number of on track students 20 Number of off track number 20 Canvas garde 50%age | Due to login access issue for first 4 days students might not able to be on track | Talked with the generation team and got access for canvas and code academy for students on 5th day of week 1 |  | G: 85% and above
Y: 75%-85%
R: Below 75%
SSC Assessment Preparation | Average of Last assessment (If applicable): |  |  |  | G: 85% and above
| Participants in G: |  |  |  | Y: 75%-85%
| Participants in Y: |  |  |  | R: Below 75%
Participants in R:ipants in R:
Mentorship Session | Name: |  |  |  | G: 85% and above
Y: 75%-85%
R: Below 75%
Placement | No of learners aligned for placement: |  |  |  | G: 85% and above
| No of learners willing to migrate: |  |  |  | Y: 75%-85%
| No of learner unwilling to migrate (with reasons): |  |  |  | R: Below 75%
2 key Takeaways from the week | BSM TOPICS: Growth Mindset, Persistent, Proactiveness, Communication
welcome session on code academy and code foundation

## Week 3
Governance Call Summary Report Template
Batch Name as per Salesforce | JSD 01_OL_AMBER 02_Orion_Barasat | Training Partner Name | Orion Edu Tech
GC of _th Week | 2 | Present Week and Day | 2 & 10 | Total Strength | 31
Batch Start Date as per Salesforce | 14.04.2023 | Domain Trainer | R Deepika | IER Score
Batch End Date as per Salesforce | 14.07.2023 |  |  | Track (On Track/Off Track)
Batch Start Date as per Curriculum | 17.04.2023 | Assistant Trainer | Khushbu Singh | IER Score
Batch End Date as per Curriculum | 17.07.2023 |  |  | Track (On Track/Off Track)
Metric | Data | Root cause for Low/High performance | Next Steps |  | Status
Attendance | Class Average: 70% | Koushiki is suffering from small pox so she not present daily in the class. Resove,Sharmila,Anik also not present daily in class.I call them to ask reason but Resove,Sharmila not pick my call and Anik is pursuing MSc. Abhijet ,Pinki,Rajat Ghosh,Shisir,Md. Barjahan not joining the class .I call them To ask reason of not joining the class but no one pick my call. | Try to talk and convience them. Drop the students if not join in next coming weeks. |  | G: 85% and above
| Participants in G: 22 |  |  |  | Y: 75%-85%
| Participants in Y: 4 |  |  |  | R: Below 75%
Participants in R: 5
Punctuality | Class Average: 70% | Koushiki is suffering from small pox so she not present daily in the class. Resove,Sharmila,Anik also not present daily in class.I call them to ask reason but Resove,Sharmila not pick my call and Anik is pursuing MSc. Abhijet ,Pinki,Rajat Ghosh,Shisir,Md. Barjahan not joining the class .I call them To ask reason of not joining the class but no one pick my call. | Try to talk and convience them..Drop the students if not join in next coming weeks. |  | G: 85% and above
| Participants in G: 22 |  |  |  | Y: 75%-85%
| Participants in Y: 4 |  |  |  | R: Below 75%
Participants in R: 5
Grooming | Class Average: 70% | Rajat Hussain do not response in class and Masuda Khatoon not join in proper timing and not doing any assignments. Koushiki is suffering from small pox so she not present daily in the class. Resove,Sharmila,Anik also not present daily in class.I call them to ask reason but Resove,Sharmila not pick my call and Anik is pursuing MSc. Abhijet ,Pinki,Rajat Ghosh,Shisir,Md. Barjahan not joining the class .I call them To ask reason of not joining the class but no one pick my call | Talked with the student who is having network issue and told them to take synchronous session in mobile and asychronous session in laptop. For login issue we contacted generation team and got access for canvas and code academy for students |  | G: 85% and above
| Participants in G: 20 |  |  |  | Y: 75%-85%
| Participants in Y: 6 |  |  |  | R: Below 75%
Participants in R: 5
Dropout | Dropouts of week:8 | Proloy Saha, UPAM MAZUMDER, Rajib Mohanta, Shalini Roy, Shatabdi Chouhan, Supriya Pahan, MAMUN MAHAMMAD, SERFUL SK, Abu Raihan Mondal |  |  | G: 85% and above
| Total Dropouts till week:9 |  |  |  | Y: 75%-85%
| No Show:1 |  |  |  | R: Below 75%
Performance | Behavioral Skill |  |  |  | G: 85% and above
| Class Average 2.85 |  |  |  | Y: 75%-85%
| Participants in G: 22 |  |  |  | R: Below 75%
Participants in Y: 4
Participants in R: 5
| Mindset Skill |  |  |  | G: 85% and above
| Class Average 2.85 |  |  |  | Y: 75%-85%
| Participants in G: 22 |  |  |  | R: Below 75%
Participants in Y: 4
Participants in R: 5
| Technical Skill |  |  |  | G: 85% and above
| Class Average : 9.0 |  |  |  | Y: 75%-85%
| Participants in G : 22 |  |  |  | R: Below 75%
Participants in Y : 4
Participants in R: 5
Curriculum Progression | Curriculum day: Monday to Friday |  |  |  | G: 85% and above
| Week: 2 |  |  |  | Y: 75%-85%
| Day: 10 |  |  |  | R: Below 75%
On tract as per session plan- yes
Canvas Progression: | Canvas completion 67.78%age number of on track students 22 Number of off track number 9 Canvas garde 59.3%age | Due to login access issue for first 4 days students might not able to be on track | Talked with the generation team and got access for canvas and code academy for students on 5th day of week 1 |  | G: 85% and above
Y: 75%-85%
R: Below 75%
SSC Assessment Preparation | Average of Last assessment (If applicable): |  |  |  | G: 85% and above
| Participants in G: |  |  |  | Y: 75%-85%
| Participants in Y: |  |  |  | R: Below 75%
Participants in R:ipants in R:
Mentorship Session | Name: |  |  |  | G: 85% and above
Y: 75%-85%
R: Below 75%
Placement | No of learners aligned for placement:22 | Resove,Sharmila,Anik also not present daily in class.I call them to ask reason but Resove,Sharmila not pick my call and Anik is pursuing MSc. Abhijet ,Pinki,Rajat Ghosh,Shisir,Md. Barjahan not joining the class .I call them To ask reason of not joining the class but no one pick my call. | Try to talk and Convience them. Drop the students if not join in next coming weeks. |  | G: 85% and above
| No of learners willing to migrate:22 |  |  |  | Y: 75%-85%
| No of learner unwilling to migrate (with reasons):9 |  |  |  | R: Below 75%
2 key Takeaways from the week | BSM TOPICS:Future Orientation,Listening,Orientation to Detail,Speaking,Teamwork,Handling Initail Failure,Proactiveness,Intro to Scorecard
Technical Topics:Code Foundations,Learn The Command Line